## Reports
{WIP] | Regression |  | QUALITY ENGINEER
TEST PLAN | N/A |  | DATE STARTED | 2024-08-07 |  | TIME PLANNED
TEST ENVIRONMENT | Staging |  | DATE ENDED | 2024-08-07 |  | TIME EXECUTED
TEST SUMMARY
TEST CASE | PASSED | FAILED | DEFERRED | UNCOVERED | % EXECUTED | TOTAL PLANNED | TOTAL TESTS
Login | 11 | 0 | 0 | 0 | 100% | 11 | 11
Sales | 12 | 0 | 0 | 2 | 100% | 12 | 14
Purchase | 40 | 0 | 0 | 2 | 100% | 40 | 42
Warehouse | 20 | 0 | 0 | 0 | 100% | 20 | 20
Cashier | 28 | 0 | 0 | 1 | 100% | 28 | 29
Dashboard | 10 | 0 | 0 | 2 | 85.71% | 12 | 14
Accountancy | 24 | 0 | 0 | 0 | 100% | 24 | 24
Report | 44 | 0 | 0 | 3 | 71.21% | 63 | 66
Settings | 10 | 0 | 0 | 0 | 76.92% | 13 | 13
API | 2 | 0 | 0 | 0 | 100% | 2 | 2
APP VERSIONS |  |  | APP LINK |  | USERNAME | PASSWORD | ROLES
PHARMACY DOMAIN |  |  |  |  | admin | admins
API
TEST PROGRESS
ON GOING | SKIPPED | DONE | COVERED TESTS | TOTAL TESTS
24 | 10 | 201 | 225 | 235
REASON FOR DEFERRED AND UNCOVERED CASES
CONCLUSION

## Revision
DATE | TITLE | DESCRIPTION | REVISED BY
2023-07-13 | Inofarma_Test_Case_v2.01 | Intial Test Case for the new Garuda app | Ihwanu Thoriq
2023-08-08 | Inofarma_Test_Case_v2.02 | Added Cashier test cases | Ihwanu Thoriq
2023-09-06 | Inofarma_Test_Case_v2.03 | Added Dashboard test cases | Ihwanu Thoriq
2023-10-02 | Inofarma_Test_Case_v2.04 | Added Report Navigation Cases | Ihwanu Thoriq
2023-10-12 | Inofarma_Test_Case_v2.05 | Added Accountancy, Login and Setting Cases | Ihwanu Thoriq
2024-04-25 | Inofarma_Test_Case_v2.06 | Added Puchase test cases - GR (Good Receives) from SwipeRx - GR from Telukgong | Ihwanu Thoriq
2024-06-26 | InofarmaV2_Test_Case_v2.07 | - Report improvement - COGS and Inventory value improvement - GAR-REP 022 to 033 | ihwanu Thoriq
2024-06-28 | InofarmaV2_Test_Case_v2.08 | Fixing Formating : - Text Style - Conditional Format for status - Alternating color | Iqbal/ Ian
2024-07-08 | InofarmaV2_Test_Case_v2.09 | Added Report Navigation Cases : - Rounded in sales report by product - Total discount and total nett sales in sales report by product - Row of pembulatan - Integration report Report by invoice and Report by payment type - Integration report Report by product and Report by product type - Integration P&L Report, sales report by product, sales report by invoice - Integration GR Total purchase with report by product Updated the writing format of test scenarios in Report | Iqbal
2024-07-09 | InofarmaV2_Test_Case_v2.10 | Remove PRE-REQUISISTE column Add Test Case : - Report - Sale - Per Return Test Case - Report - Inventory - Probability Add Checklist Data report | Iqbal
2024-07-17 | InofarmaV2_Test_Case_v2.11 | Add Test Case : - Remove Tab Application - Hide Item Kit - Laporan - Persediaan - per persediaan | Iqbal
2024-07-29 | InofarmaV2_Test_Case_v2.12 | Hide Report : - GAR-REP-043-049 - Hide sales report by shift - Hide Sales report by Cashier - Hide sales report by drug classification - Hide Purchase Report by classification - Hide Sales Repor by product type - Hide Sales report by audit - Hide Sales Report by void per item | Thoriq
2024-07-30 | Garuda_InofarmaV2_Test_Case_v3.00_<release> | Format Update: - updated test results selection based on index (with legend) | John Ian Biligan
2024-07-31 | Garuda_InofarmaV2_Test_Case_v3.01_<release> | GR management : - GAR-PUR 015 - 026 - Update GR - Update item - Adjust weighted average in return | Iqbal
2024-08-06 | Garuda_InofarmaV2_Test_Case_v3.02_<release> | Stock Opname : - GAR-WAR 010 - 012 - Adjust column Harga to Nilai Persediaan - Nilai persedian get from Item Price / Weighted Average | Iqbal
2024-08-07 | Garuda_InofarmaV2_Test_Case_v3.03_<release> | API Integrations : - GAR-API-001 - 002 - Master SKU data sync | John Ian Biligan
2024-08-13 | Garuda_InofarmaV2_Test_Case_v3.04_<release> | Hide Report : - GAR-REP-049 - Hide Warehouse Pareto Report Hide VAT : - GAR-SAL 014 - Hide VAT button Hide Return : - GAR-PUR 025 - Hide Return feature - Remove Testcase for return | Iqbal
2024-08-23 | Garuda_InofarmaV2_Test_Case_v3.05_<release> | Re Enable Return : - GAR-PUR 025 - 028 - Unhide Return feature - Add Testcase for return Unhide Ledger Report : - GAR-REP-049 - 051 - Unhide Ledger - Add ledger details Addit GR Payment Validation : - GAR-PUR 029 - 030 - Bank Balance or Cash Balance is not equal or more than the total payment Adjust Purchase report per product - GAR-REP-052 - 054 - Adding some column - Export report Total discount between sales report per product, P&L, and per invoice - GAR-REP-055 Aligning Report Balance and Trial Balance : - GAR-REP-056 - 057 - Add new column - Two report have same value Unhide Paretor report - Update GAR-REP-016 | Iqbal
2024-08-30 | Garuda_InofarmaV2_Test_Case_v3.06_<release> | Responsive stock opname table - GAR-WAR 013 Product selection using keyboard - GAR-POS 29 Verification button on GR while updating price - GAR-PUR 031 Can't delete GR from previous month - GAR-PUR 032 Update purchase price - GAR-PUR 032 Merge same batch and ED in SO and GR - GAR-PUR 033 - GAR-WAR 014 Load more button in Report Supply - Probability - GAR-REP-058 | Iqbal
2024-08-30 | Garuda_InofarmaV2_Test_Case_v3.07_<release> | Bug Fixing Ledger - GAR-REP-059 - GAR-REP-061 | Iqbal
2024-09-13 | Garuda_InofarmaV2_Test_Case_v3.08_<release> | - Separated cases to smaller one Added: - GAR-ACC 008 - GAR-ACC 021 - GAR-REP 062 - GAR-REP-065 Updated test scenario: - GAR-ACC 004 | Anjani
2024-09-18 | Garuda_InofarmaV2_Test_Case_v3.09_<release> | Added: - GAR-PUR 034 - GAR-PUR 042 - GAR-WAR 015 - GAR-WAR 021 | Anjani

## Modules
TEST CASE ID | SCOPE | DESCRIPTION
GAR-PUR | Purchase | Stock, Product management feature
GAR-SAL | Sales | Product List, Promo and Contact
GAR-REP | Report_Nav | Selling, Purchasing, Warehouse, Accounting report
GAR-WAR | Warehouse | Stock Opname, Current Stock, Moving Stock, Warehouse list
GAR-DASH | Dashboard | Dashboard to get some description about pharmacy selling, stock, and report management
GAR-ACC | Accountancy | Accounting feature
GAR-POS | Cashier | Point of Sales feature
GAR-SET | Settings | System Settings
GAR-LOG | Login | Login Page
GAR-API | API | API related calls (sync data)

## API
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-API-001 | Master SKU Upload | 1. Get data from product team or developer (latest or edited) | 1. Call endpoint /api/v4/core/master-sku/bulk-upload | Should be able to update the master sku product database table
PASSED | GAR-API-002 | Pharmacy Sync | 1. Update data based on GAR-API-001 **test can start from zero product | 1. Call endpoint /api/v4/core/master-supplier/pharmacy-sync | Should be able to update product list based on the new data

## Login
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-LOG 001 | Login Page | Automatically set by the system | 1. Go to Login page 2. login using credential 3. credential username admin 4. credential password admins | Pharmacy able to login using default credential username and password
PASSED | GAR-LOG 002 | Login Page - Login with new username and password | Pharmacy must set new credential username and password using super user | 1. go to login page 2. login using new credential username and password | Pharmacy able to login using new credential username and password
PASSED | GAR-LOG 003 | Login Page - Login with new username and password with cashier group | Pharmacy must set new credential username and password with cashier group | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with cashier group | Pharmacy able to lgoin using new credential username and pasword with cashier group
PASSED | GAR-LOG 004 | Login Page - Login with new username and password with warehouse group | Pharmacy must set new credential username and password with warehouse group | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with warehouse group | Pharmacy able to lgoin using new credential username and pasword with warehouse group
PASSED | GAR-LOG 005 | Login Page - Login with new username and password with accounting group | Pharmacy must set new credential username and password with accounting group | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with cashier group | Pharmacy able to lgoin using new credential username and pasword with accounting group
PASSED | GAR-LOG 006 | Login Page - Login page with privilege setting on cashier group | Pharmacy must set new privilege on cashier group | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with cashier group | Pharmacy able to set privilege on cashier group
PASSED | GAR-LOG 007 | Login Page - Login page with privilege setting on warehouse group | Pharmacy must set new privilege on cashier group | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with warehouse group | Pharmacy able to set privilege on warehouse group
PASSED | GAR-LOG 008 | Login Page - Login page with privilege setting on accounting group | Pharmacy must set new privilege on accounting group | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with accounting group | Pharmacy able to set privilege on accounting group
PASSED | GAR-LOG 009 | Login page - Login page with new group | Pharmacy must set new group of user | 1. login to login page 2. login using new credential username and password 3. make new credential username and password 4. group with new group | Pharmacy able to set new group of user and able to login with it
PASSED | GAR-LOG 010 | Login page - Wrong username pop up | Parmacy input the wrong username and password | 1. login page 2. input wrong username and password 3. there notification | Pharmacy able to see notification "Username atau Password tidak ditemukan"
PASSED | GAR-LOG 010 | Login page - Wrong username pop up | Parmacy input the wrong username and password | 1. login page 2. input wrong username and password 3 times 3. there notification | Pharmacy able to see notification "Username atau Password tidak ditemukan. Silakan kontak support@inolabs.net untuk mendapatkan username dan password anda."

## Accountancy
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-ACC 001 | Accounting - Journal | 1. Pharmacy is in Accountancy 2. Pharmacy has transacion on cashier, reception and stock opname | 1. click on journal | 1. should shows all the transaction journal from cashier, reception and stock opname
PASSED | GAR-ACC 002 | Accounting - Income and expenses tranaction | 1. Pharmacy create income or expense that not created from cashier, reception and stock opname module 2. Pharmacy is in Accountancy | 1. click on income and expenses "pemasukan dan pengeluaran" 2. choose between inputing income or expenses 3. enter the description "deskripsi" 4. enter the amount 5. choose the category "kategori" 6. choose the accunt or payment method between cash or bank 7. submit | 1. should create new journal on the accounting report 2. should change the total amount of accounting report
PASSED | GAR-ACC 003 | Accounting - Account | 1. Pharmacy create new account beside of mandatory account that created by system 2. Pharmacy is in Accountancy - Akun | 1. click on accountancy "akuntansi" 2. click on akun "account" 3. add new account 4. choose the type of account 5. input the number code of the account 6. input the name of the account 7. save | 1. should create new account on accountancy module 2. should create payable acoount on accountancy module
PASSED | GAR-ACC 004 | Accounting - Beginning ballance | 1. Pharmacy make total amount are ballance between debet dan credit 2. Pharmacy is in Accountancy - Beginning balance | 1. fill the description and date 2. fill the account with amount 3. save | 1. should add the amount of beginning ballance on the accounting report
PASSED | GAR-ACC 005 | Accounting - Other Income and expense | Pharmacy is in Accounting - other income and expense | 1. go to accountancy --> pemasukan dan pengeluaran 2. click pengeluaran / pemasukan 3. input description, amount, choose the acoount, --> click verification | pharmacy able to input other income and expense
PASSED | GAR-ACC 006 | Accounting - Journal | Pharmacy is in Accounting - Jurnal | 1. go to journal --> filter the date 2. search the journal | pharmacy able to see the other income and expense journal
PASSED | GAR-ACC 007 | Accounting - Account - 6120 | Journal for Stock Adjustment | 1. go to journal --> filter the date 2. serach the journal for stock adjustment (Stock Opname) | 1. should has new COA 6120 - Penyesuaian stock
PASSED | GAR-ACC 008 | Accounting - Journal - New transaction | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'Add new transaction button' 3. fill in the 'description' and choose the 'date' for the transaction 4. click on the 'add new line' 5. choose the account in the dropdown, fill the description, input the debit/credit amount (the credit amount has to be the same as the credit amount) 6. click the 'save' button | a new journal transaction has successfully been added
PASSED | GAR-ACC 009 | Accounting - Journal - Failed new transaction | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'Add new transaction button' 3. fill in the 'description' and choose the 'date' for the transaction 4. click on the 'add new line' 5. choose the account in the dropdown, fill the description, input the debit/credit amount (the credit amount has to be different than the credit amount) 6. click the 'save' button | a new journal transaction hasn't been made and the system notifies that the credit has to be equal with the debit amount
PASSED | GAR-ACC 010 | Accounting - Journal - Other failed new transaction | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'Add new transaction button' 3. leave out the 'description' and the 'date' field 4. click on the 'add new line' 5. choose the account in the dropdown, fill the description, input the debit/credit amount 6. click the 'save' button | a new journal transaction hasn't been made and the system notifies that the description and date field is required to fill
PASSED | GAR-ACC 011 | Accounting - Journal - Search | Pharmacy is in accounting - journal | 1. go to journal 2. choose the starting and ending data date 3. click the 'show' button | should shows all the transaction journal at the selected date period
PASSED | GAR-ACC 012 | Accounting - Journal - Download excel | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'Excel' button | successfully download the transaction journal excel file
PASSED | GAR-ACC 013 | Accounting - Journal - Pending data sync | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'view data' button | shows the pending data syncronization
PASSED | GAR-ACC 014 | Accounting - Journal - Transaction detail | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'detail' button on the action column from the journal transaction table | shows the detail (includes account, description, debit, credit amount) of the selected journal transaction
PASSED | GAR-ACC 015 | Accounting - Journal - Download transaction file | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'download journal' button on the action column from the journal transaction table | successfully download the selected transaction journal file
PASSED | GAR-ACC 016 | Accounting - Journal - Edit transaction | Pharmacy is in accounting - journal | 1. go to journal 2. click on the 'edit' button on the action column from the journal transaction table 3. make edits in the transaction journal 4. click the 'save' button | an edit on the transaction journal has been made
PASSED | GAR-ACC 017 | Accounting - Journal - Delete transaction | 1. Pharmacy is in accounting - journal 2. Pharmacy has manually added a journal transaction | 1. go to journal 2. click on the 'delete' button on the action column from the journal transaction table 3. make edits in the transaction journal 4. click the 'save' button | the transaction journal has been deleted | Need to refresh after clicking the save button
PASSED | GAR-ACC 018 | Accounting - Income and expenses transaction - Delete transaction | 1. Pharmacy is in accounting - income and expenses 2. Pharmacy has manually added an income and expenses transaction | 1. go to income and expenses 2. choose the transaction that is going to be deleted with the checkbox 3. click the 'delete' button | income and expense transaction has been deleted
PASSED | GAR-ACC 019 | Accounting - Income and expenses tranaction - Search transaction | 1. Pharmacy is in accounting - income and expenses | 1. go to income and expenses 2. choose the starting and ending data date and other dropdown details 3. click 'search' button | should shows all the income and expenses at the selected date period
PASSED | GAR-ACC 020 | Accounting - Account - Edit account | 1. Pharmacy is in accounting - account | 1. go to account 2. make edits on the account 3. click 'save' button | an edit on the account has been made
PASSED | GAR-ACC 021 | Accounting - Account - Delete account | 1. Pharmacy is in accounting - account 2. Pharmacy has manually added an account | 1. go to account 2. click 'delete' button on the account that has been manually added 3. click 'save' button | the account has been deleted
PASSED | GAR-ACC 022 | Accounting - Account - Download excel | Pharmacy is in accounting - account | 1. go to account 2. click on the 'Excel' button | successfully download the account excel file
PASSED | GAR-ACC 023 | Accounting - Beginning ballance - Failed to add beginning ballance amount | Pharmacy is in accounting - beginning balance | 1. go to beginning balance 2. leave out the description & date field 3. fill the account with amount 4. click the 'save' button | Beginning balance amount failed to add with the system notifies that the description and date field is required to fill
PASSED | GAR-ACC 024 | Accounting - Beginning ballance - Other failed to add beginning ballance amount | Pharmacy is in accounting - beginning balance | 1. go to beginning balance 2. fill the description & date field 3. fill the account with amount (credit and debit different amount) 4. click the 'save' button | Beginning balance amount failed to add with the system notifies that the credit has to be equal with the debit amount

## Dashboard
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-DASH 001 | Dashboard - Customer list |  | 1. go to dashboard 2. click on customer (pelanggan) 3. go to customer list | Pharmacy able to access customer list page by clicking customer (pelanggan) button on dashboard
PASSED | GAR-DASH 002 | Dashboard - Product lsit |  | 1. go to dashboard 2. click on product 3. go to product list | Pharmacy able to access product list page by clicking product button on dashboard
PASSED | GAR-DASH 003 | Dshboard - Transaction List |  | 1. go to dashboard 2. click on total Transaction 3. go to transaction list | Pharmacy able to access transction report page by clicking total transction button on dashboard
PASSED | GAR-DASH 004 | Dashboard - gross incomechart | Pharmacy must make a transaction on POS | 1. go to dashboard 2. see the gross income chart 3. go to report --> accounting report --> income statement 4. make sure the amount of income chart on the dashboard taken from income statement itself | Pharmacy able to see the gross income chart on the dashboard based on the income statement
| GAR-DASH 005 | Dashboard - Monthly Gross Income chart |  | 1. go to dashboard 2. see the gross income chart 3. go to report --> accounting report --> income statement 4. make sure the amount of income chart on the dashboard taken from income statement itself 5. filtered by last 6 months | Pharmacy able to see the gross income chart on the dashboard based on the income statement
PASSED | GAR-DASH 006 | Dashboard - Current Activity | Pharmacy must done with this activities : 1. set product to sell / unsell 2. add product 3. add customer list 4. delete product | 1. go to dashboard 2. see the current acitvity table 3. click on details (selengkapnya) | Pharmacy able to see the current activities
PASSED | GAR-DASH 007 | Dashboard - Best sold product for last 3 month | Pharmacy must make transactions on POS | 1. go to dashboard 2. see the best sold product for the last 3 months column 3. click on details (selengkapnya) | Pharmacy able to see best sold product for the last 3 months
PASSED | GAR-DASH 008 | Dashboard - Expired Product list | Pharmacy must set the expriy date of every product | 1. go to dashboard 2. see the expired product list 3. click on the amount button in the expired product list 4. go to expired product list | Pharmacy able to see the expired product list
UNCOVERED | GAR-DASH 009 | Dashboard - Minimum Stock List | Pharmacy must set the minimum stcok of every product | 1. go to dashboard 2. click on the minimum stock list 3.go to defecta module | Pharmacy able to see the product that reach the minimum stock
PASSED | GAR-DASH 010 | Dashboard - empty stock list | Product on the list are zero stock | 1. go to dashboard 2. click on the zero stock 3. go to stock product report list | Pharmacy able to see the product that reach zero
PASSED | GAR-DASH 011 | Dashboard - Product search | Product searched are taken from POS information | 1. go to dashboard 2. go to searched product list 3. click on details (selengkapnya) | Pharmacy (POS) able to add searched product that are not on the pharmacy product list
UNCOVERED | GAR-DASH 012 | Dashboard - Top seller list | Pharmacy must make transactions on POS | 1. go to dashboard 2. go to to seller list 3. click on details (selengkapnya) | Pharmacy able to see top seller based on the credential username
PASSED | GAR-DASH 013 | Dashboard - Last stock opname history | Pharmacy must make Stock opname for some product | 1. go to dashboard 2. go to last stock opname list 3. click on details 4. go to history stock opname list module | Pharmacy able to see the list of last stock opname made by user
| GAR-DASH 014 | Dashboard - List of Stock Opname minus | Pharmacy must make Stock opname for some product | 1. go to dashboard 2. go to list of stock opname that minus 3. click on details 4. go to history stock opname list module | Pharmacy able to see the list of last stock opname made by user

## Cashier
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-POS 01 | Cashier - Open Shift | Pharmacy must login with username credential | 1. go to cashier 2. input nominal to open shift (pittycash) | 1. Pharmacy able to use POS 2. pittycash are included with the total amount of cash when the shift closed 3. Shift are same with the login page shift (morning/afternoon/night)
PASSED | GAR-POS 02 | Cashier - Input product name | Pharmacy must input product name in the ineventory management | 1. go to cashier 2. open POS 3. Input Product name 4. autocomplete are shown when alfabeth are typing on the product name column | Pharmacy able to input product name in POS
PASSED | GAR-POS 03 | Cashier - Input amount of product | Pharmacy are input the product stock in the inventory management first | 1. go to cashier 2. open POS 3. input product name 4. input amount of product | Pharmacy able to get some product amount
PASSED | GAR-POS 04 | Cashier - Package | Pharmacy are set the product package in the invenotry management Pharmacy able to set the product package more than 1 package | 1. Open POS 2. input product name 3. input amount of product 4. choose product package | Pharmacy able to get the product package taken from product data list
PASSED | GAR-POS 05 | Cashier - Discount Product | Pharmacy input product name etc before inputting the product discount | 1. Open POS 2. Input product name 3. input amount of product 4. Choose product package 5. input discount of the product | Pharmacy able to input product discount (Rupiah)
PASSED | GAR-POS 06 | Cashier - Cash Transaction | Pharmacy must has product data list and product stock | 1. open POS 2. input product name 3. input amount of product 4. choose product package 5. input discount or not 6. go to cash column 7. input cash payment 8. click pay | Pharmacy able to make cash transaction
PASSED | GAR-POS 07 | Cashier - Debt transction | Pharmacy must has product data list and product stock | 1. open POS 2. input product name 3. input amount of product 4. choose product package 5. input discount or not 6. go to cash column 7. input cash with 0 8. click pay | Pharmacy able to mak debt transcation
PASSED | GAR-POS 08 | Cashier - Online payment | Pharmacy must has product data list and product stock Pharmacy must set online payment in the setting module | 1. open POS 2. input product name 3. input amount of product 4. choose product package 5. input discount or not 6. go to cash column 7. go to debet/kredit/online payment 8. choose the bank, input owner name, input bank account number 9, click OK 10, click PAY | Pharmacy able to use online/bank payment
PASSED | GAR-POS 09 | Cashier - Snooze Transaction | Pharmacy must input product first | 1. open POS 2. input product name 3. input amount of product 4. choose product package 5. input discount or not 6. tap (delete) or click tunda | Pharmacy able to snooze the transaction and call it back
PASSED | GAR-POS 10 | Cashier - Call the snooze transaction | Pharmacy input snooze | 1. go to POS 2. click daftar tunda (snooze list) 3. search the invoice/ by product 4. click action --> open transaction | Pharmacy able to snooze and call it back
PASSED | GAR-POS 11 | Cashier - Delete snooze tranasction | Pharmacy input snooze transaction | 1. go to POS 2. click daftar tunda (snozelist) 3, search the list 4. choose hapus 5. checklist the snooze that want to delete 6. click hapus data (delete data) | Pharmacy able to delete the snooze list
PASSED | GAR-POS 12 | Cashier - Additional Cost |  | 1. open POS 2. input product name 3. input amount of product 4. choose product package 5. input discount or not 6. click additional cost 7. there some information able to add 8. add due date 9. adding discount of whose transaction (IDR/%) 10. adding tuslah/embalage/ongkir/inspection fees 11. save 12. make a payment | Pharmacy able to input additional cost
PASSED | GAR-POS 13 | Cashier - Add new customer data |  | 1. open POS 2. go to customer (pelanggan) 3. click on plus button 4. input customer name, phone number and addres 5. save | Pharmacy able to add customer data from POS
PASSED | GAR-POS 14 | Cashier - Add new doctor data |  | 1. open POS 2. go to doctor (dokter) 3. click on plus button 4. input customer name, phone number and addres 5. save | Pharmacy able to add new doctor data from POS
UNCOVERED | GAR-POS 15 | Cashier - Transaction Limit | Pharmacy has 200 or more product list and has stock for every product | 1. Open Cashier 2. Input Product Name 3. check the limit till 200 product
PASSED | GAR-POS 16 | Cashier - Void Transaction | Pharmacy done the transaction | 1. Open Cashier 2. go to transaction list 3. search the invoice number 4. go to action 5. choose void 6. void must be approved by superuser (exp : admin) 7. input password of superuser 8. process | Pharmacy able to void the transaction
PASSED | GAR-POS 17 | Cashier - Reorder | Pharmacy done the transaction Pharmacy has stock for each reorder product | 1. Open Cashier 2. go to transaction list 3. search the invoice number 4. go to action 5. choose Reorder 6. make a payment | Pharmacy able to reordering done transaction
PASSED | GAR-POS 18 | Cashier - Print Receipt | Pharmacy done th transction | 1. Open Cashier 2. go to transaction list 3. search the invoice number 4. go to action 5. choose Print receipt (cetak nota) | Pharmacy able to reprinting receipt
PASSED | GAR-POS 19 | Cashier - Details | Pharmacy done th transction | 1. Open Cashier 2. go to transaction list 3. search the invoice number 4. go to action 5. choose Detail | Pharmacy able to see detail from done transaction
PASSED | GAR-POS 20 | Cashier - Buyer Category | Pharmacy must set buyer category | 1. Open Cashier 2. input product 3. input Customer name 4. make sure selling price are changed based on customer name | Pharmacy able to set buyer category and has several prices based on buyer category
PASSED | GAR-POS 21 | Cashier - Pop Up Open Shift |  | 1. Open cashier 2. input modal (initial cash) 3. save 4. pop up confirmation | Pharmacy able to see the pop up confirmation about login "Anda login sebagai ADMIN dan akan MEMBUKA Shift Sore 19-10-2023 dengan MODAL Rp0?"
PASSED | GAR-POS 22 | Cashier - ED Pop Up Notification | Pharmacy has expired product on Stock Opname | 1. input product name 2. input amount and choose the package 3. product are expired --> there is a pop up | Pharmacy able to see pop up of expired product "Produk telah kadaluarsa. Mohon lakukan Stock Opname untuk memperbaiki stok product."
PASSED | GAR-POS 23 | Cashier - Available stock POP UP | Product are not enough | 1. Input product name, amount, and package 2. amout product are not available 3. there is a pop up notification | Pharmacy able to see pop up of available product stock "Sisa Stok: 5 Pot Kaca Stok telah kadaluarsa: 10 Pot Kaca"
PASSED | GAR-POS 24 | Cashier - Empty Stock POP UP | Product are not avaiable | 1. input product name, amount, and package 2. there is a pop up notification about empty stock | Pharmacy able to see pop up "Sisa Stok: 0 Pot Kaca Stok telah kadaluarsa: 0 Pot Kaca "
PASSED | GAR-POS 25 | Cashier - Success transaction |  | 1. Input product name, amount, and package 2. input cash --> payment 3. there is a pop up notification | There is pop up "Lanjutkan pembayaran dengan Total Tagihan Rp 2.410?"
PASSED | GAR-POS 26 | Cashier - Process the transaction pop up |  | 1. input product name, amount, and package 2. input cash --> payment 3. after show the pop up nofirmation --> lanjutkan | There is pop up after the transaction "Transaksi telah disimpan. Kembalian Rp 90"
PASSED | GAR-POS 27 | Cashier - Close shift |  | 1. go to shortcut 2. close chift 3. there pop up about to close shift | There is pop up about to close the shift "OS memiliki daftar tunda. Tetap ingin menutup shift?"
PASSED | GAR-POS 28 | Cashier - Round up | pharmacy input product to the bucket | 1. cashier --> input product --> amount 2. total amount are roundup | rounding up of the total checkout in cashier transaction
PASSED | GAR-POS 29 | Cashier - Select product with keyboard |  | 1. cashier --> input product name | Pharmacies able to select product suggestion using keyboard

## Sales
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-SAL 001 | Sales - Product - Download Sample product excel |  | 1. go to sales 2. go to product 3. go to import --> new product --> click sample product button 4. see the excel file | Pharmacy able to download sample product excel (Column are updated)
PASSED | GAR-SAL 003 | Sales - Product - Export product list | Pharmacy are make new reception twice for some product | 1. go to sales 2. go to product 3. click export excel | Pharmacy able to make sure that excel of product list showing product stock same with system stock
PASSED | GAR-SAL 004 | Sales - Product - Buyer Category |  | 1. go to sales 2. go to contact 3. buyer category --> make new buyer category 4. go to product --> click buyer category 5. choose buyer category type --> choose apply to all product 6. click apply | Pharmacy able to make new buyer category and applied it with the new product
UNCOVERED | GAR-SAL 005 | Sales - Product - Delete Product | Pharmacy must input product first | 1. go to sales 2. go to product 3. go to option --> delete product 4. make sure product are deleted | Pharmacy able to delete product | Not available in pharmacy 4
UNCOVERED | GAR-SAL 006 | Sales - Product - Duplicate Product | Pharmacy must input product first | 1. go to sales 2. go to product 3. go to option --> duplicate product 4. make sure product are duplicated | Pharmacy able to duplicate product | Not available in pharmacy 4
PASSED | GAR-SAL 007 | Sales - Product - Sets sold | Pharmacy must input product first | 1. go to sales 2. go to product 3. go to option --> sets sold 4. make sure product can be sold in POS | Pharmacy able to sets the product sold
PASSED | GAR-SAL 008 | Sales - Product - Rounded Selling price | Pharmacy must input product first | 1. go to sales 2. to to product 3. input new product 4. input selling price 5. save --> make sure slling price rounded | Pharmacy able to input product with rounded selling price
PASSED | GAR-SAL 009 | Sales - Product - Set default Package | Pharmacy must input product and has 2 selling package | 1. go to sales 2. go to product 3. click option 4. set default package 5. choose the package 6. click save | Pharmacy able to change default package to sold
PASSED | GAR-SAL 010 | Sales - Product - Add contact |  | 1. go to contact 2. add new contact 3. fill the column 4. save | Pharmacy able to add new contact / customer
PASSED | GAR-SAL 011 | Sales - Product - Overview | Pharmacy must input contact of customer | 1. go to contact 2. click action 3. click monitor icon 4. there pop up of overview | Pharmacy able to see overview pop up
PASSED | GAR-SAL 012 | Sales - Product - Product List |  | 1. go to Product List 2. make sure product list showing after GR | Pharmacy able to see product list
PASSED | GAR-SAL 013 | Sales - Product - Item Kit |  | 1. go to sales 2. go to product | The button Tambah Item Kit not displayed
PASSED | GAR-SAL 014 | Sales - Product - Edit Product - VAT button | Pharmacy must input product first | 1. go to sales 2. go to product 3. edit product | VAT button should be hidden
PASSED | GAR-SAL 015 | Sales - Product - Edit Product - purchase price | Pharmacy must input product first | 1. go to sales 2. go to product 3. edit product | Pharmacy able to update purchase price (+PPN)

## Purchase
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
UNCOVERED | GAR-PUR 001 | Purchase - Purchase Order - (Vania Pharmacy only) | Pharmacy is in Purchase - Booking Page | 1. login to inofarmapos.com 2. go to purchase "pembelian" 3. click on purchase "pemesanan" 4. make a new purchase "pemesanan baru" 5. choose purchase to "to supplier" or "to branch" 6. input supplier name 7. choose to make purchase number manually or automatically 8. input purchase number 9. input date of purchase 10. choose receptor warehouse 11. input product, amount of purchase, choose package, input buying price 12. save "simpan" | 1. Should show a notification that order with transaction number has been saved 2. Should open a pop-up window with printable order summary
UNCOVERED | GAR-PUR 002 | Purchase - GR - (Vania Pharmacy only) | Pharmacy is in Purchase - Receipt Page | 1.login to inofarmapos.com 2. go to purchase "pembelian" 3. click on reception "penerimaan" 4. click new reception "penerimaan baru" 5. input supplier name 6. choose type of reception "cash" or "credit" 7. input faktur number 8. input date of faktur 9. input date of product reception 10. input due date of payment 11. choose type of reception "common" "V2" or "V3" 12. choose warehouse 13. input product name, amount of reception, choose the package, input expired date, input batch number, input buying price, input discount 14. click save | 1. should open a pop-up window with printable reception summary 2. should save a reception details on the reception window 3. should save the amount of reception details in inkaso window
PASSED | GAR-PUR 003 | Purchase - Supplier | Pharmacy is in Purchase - Suppplier | 1. login to inofarmapos.com 2. go to purchase "pembelian" 3. click on supplier 4. click on add item "tambah item" 5. input the name of supplier, phone number, and etc than save the data 6. click save | 1. should save the supplier details on supplier window 2. supplier name should shows on the purchase and reception supplier column 3. supplier name should shows on the purchase report
PASSED | GAR-PUR 004 | Purchase - GR from SwipeRx - New |  | 1. go to Purchase 2. go to GR 3. GR from Swipe rx 4. Save | Pharmacy able to use GR from Swiperx
PASSED | GAR-PUR 005 | Purchase - GR from SwipeRx - Uneditable |  | 1. go to GR from Swipe RX 2. make sure the delivery date are uneditable | Pharmacy unable to edit delivery order
PASSED | GAR-PUR 006 | Purchase - GR - Filter Delivery Order |  | 1. go to GR 2. Filter 3. input delivery order date 4. click search | Pharmacy able to filter by delivery date
PASSED | GAR-PUR 007 | Purchase - GR - Error Pop up of Puchase Order |  | 1. after saving puchase order 2. there is pop up of duplicate SP Number | Pharmacy able to see error notification ""1. after saving puchase order 2. there is pop up of duplicate SP Number "
PASSED | GAR-PUR 008 | Purchase - GR - Snooze the Puschase order transaction |  | 1. after adding product purchase order 2. click to snooze the purchase order 3. there pop up confirmation | Pharmacy able to see pop up "Anda ingin menunda transaksi ini?"
PASSED | GAR-PUR 009 | Purchase - GR - Reception - Add Product |  | 1. after adding product to reception 2. click save 3. there pop up confirmation | Pharmacy able to see pop up confirmation "Dengan menekan tombol OK maka transaksi akan disimpan ke Inkaso dan Stok?"
PASSED | GAR-PUR 010 | Purchase - GR - Reception - Save |  | 1. after saving reception 2. there pop up notification about reception | Pharmacy able to see pop up "Transaksi penerimaan dengan nomor FAKTUR 02930 berhasil disimpan."
PASSED | GAR-PUR 011 | Purchase - GR - Snooze the reception |  | 1. after adding product 2. snooze the reception 3. there pop up notification | Pharmacy able to see pop up "Anda ingin menunda transaksi ini?"
PASSED | GAR-PUR 012 | Purchase - GR - There empty ED column |  | 1. after adding some product 2. go to save 3. there pop up error of field that still empty | Pharmacy able to see pop up "ED item nomor 2 sepertinya masih salah. Mohon dicek kembali."
PASSED | GAR-PUR 013 | Purchase - Reception - Add New Item | Pharmacy create GR | 1. go to Purchase 2. go to GR 3. select GR | Pharmacy able to add new item
PASSED | GAR-PUR 014 | Purchase - Reception - Remove item | 1. Pharmacy create GR 2. The item should not transacted yet | 1. go to Purchase 2. go to GR 3. select GR | Pharmacy able to remove item
PASSED | GAR-PUR 015 | Purchase - Reception - Cancel GR | 1. Pharmacy create GR 2. The item should not transacted yet | 1. go to Purchase 2. go to GR 3. select GR | Pharmacy able to cancel GR
PASSED | GAR-PUR 016 | Purchase - GR - Create GR with same month |  | 1. go to Purchase 2. go to GR 3. Create new GR with same month 4. Save | Pharmacy able to create GR
PASSED | GAR-PUR 017 | Purchase - GR - Create GR with different month |  | 1. go to Purchase 2. go to GR 3. Create new GR with different month 4. Save | Pharmacy able to create GR in different month
PASSED | GAR-PUR 018 | Purchase - GR - Edit GR in same month | 1. Pharmacy create GR 2. The item should not transacted yet | 1. go to Purchase 2. go to GR 3. select GR with same month | Pharmacy able to edit GR
PASSED | GAR-PUR 019 | Purchase - GR - Edit GR in different month | Pharmacy create GR | 1. go to Purchase 2. go to GR 3. select GR with different month | Pharmacy not able to edit GR in different month
PASSED | GAR-PUR 020 | Purchase - GR - Edit Qty | 1. Pharmacy create GR 2. The item should not transacted yet | 1. go to Purchase 2. go to GR 3. select GR | Pharmacy able to edit Qty
PASSED | GAR-PUR 021 | Purchase - GR - Edit Price | 1. Pharmacy create GR 2. The item should not transacted yet | 1. go to Purchase 2. go to GR 3. select GR | Pharmacy able to edit price
PASSED | GAR-PUR 022 | Purchase - Edit GR (Non Swiperx) | Pharmacy Edit the GR to add new product inside the GR | after creating GR There is 2 ways to edit the GR : 1. go to GR --> go to action button --> click ubah data button 2. go to GR --> click detail data --> go to ubah data button | Pharmacy able to add new item when edit the GR from Non Swiperx Weighted Average areadjusted after edit GR
PASSED | GAR-PUR 023 | Purchase - Edit GR (Swiperx) | Pharmacy Edit the GR to add new product inside the GR | after creating GR There is 2 ways to edit the GR : 1. go to GR --> go to action button --> click ubah data button 2. go to GR --> click detail data --> go to ubah data button | Pharmacy able to add new item when edit the GR from Non Swiperx Weighted Average areadjusted after edit GR
PASSED | GAR-PUR 024 | Purchase - Edit GR (Non Swiperx) | Pharmacy Edit the GR to change qty and price | after creating GR There is 2 ways to edit the GR : 1. go to GR --> go to action button --> click ubah data button 2. go to GR --> click detail data --> go to ubah data button | Pharmacy able to change the qty and price when edit the GR from Non Swiperx Weighted Average areadjusted after edit GR
PASSED | GAR-PUR 025 | Purchase - Return - Adjust weighted average without discount | Pharmacy return GR |  | Weighted average adjusted after product returned
PASSED | GAR-PUR 026 | Purchase - Return - Adjust weighted average 1 product with pro rate discount | Pharmacy return GR |  | Weighted average adjusted after product and discount returned
PASSED | GAR-PUR 027 | Purchase - Return - Adjust weighted average 2 product with pro rate discount | Pharmacy return GR |  | Weighted average adjusted after product and discount returned
PASSED | GAR-PUR 028 | Purchase - Return Reception | 1. Pharmacy is in Purchase - return 2. user must has the reception transaction first 3. user must has the sufficient supplies of the product to return | 1. login to inofarmapos.com 2. go to purchase "pembelian" 3. click on retur "return" 4. click on faktur return "retur faktur" 5. search faktur number 6. input amount to return 7. click on verification "verifikasi" | 1. should return the amount of product to supplier 2. should decrease the product stock in the system
PASSED | GAR-PUR 029 | Purchase - GR - Credit Payment | 1. Pharmacy create GR 2. Bank Balance is not equal or more than the total payment | 1. Input GR Details 2. choose type of reception "credit" 3. click save 4. Pay GR | Pharmacy able to see notification "Saldo Bank atau Kas Anda tidak cukup untuk melakukan pembayaran Inkaso. Silakan tambahkan saldo di Akuntansi -> Saldo Awal"
PASSED | GAR-PUR 030 | Purchase - GR - Cash Payment | 1. Pharmacy create GR 2. Cash Balance is not equal or more than the total payment | 1. Input GR Details 2. choose type of reception "cash" 3. click save | Pharmacy able to see notification "Saldo Bank atau Kas Anda tidak cukup untuk melakukan pembayaran Inkaso. Silakan tambahkan saldo di Akuntansi -> Saldo Awal"
PASSED | GAR-PUR 031 | Purchase - GR - Update selling price | 1. Pharmacy create GR | 1. Click perubahan harga | Pharmacys able to verification changed price
PASSED | GAR-PUR 032 | Purchase - GR - Delete GR from previous month | 1. Pharmacy create GR |  | Pharmacys can't delete GR from previous month
PASSED | GAR-PUR 033 | Purchase - GR - Same ED and Batch |  |  | Merge stock balance
PASSED | GAR-PUR 034 | Purchase - GR - Delete GR with the "Waiting" status | Pharmacy create GR | Click on delete button in the action column | Pharmacy able to delete GR with the "waiting status"
PASSED | GAR-PUR 035 | Purchase - GR - View product data | Pharmacy create GR | Click on the view button in the product amount column | Pharmacy able to view product data
PASSED | GAR-PUR 036 | Purchase - GR - Export Excel | Pharmacy create GR | Click on the export excel button | Pharmacy able to get the GR excel file
PASSED | GAR-PUR 037 | Purchase - Reception - Pay | Pharmacy create reception | Click on the pay button in the action column, choose the payment method and insert the payment amount, click the save button | Pharmacy able to pay for the reception
PASSED | GAR-PUR 038 | Purchase - Reception - Filter | Pharmacy create reception | Insert the invoice number, choose the category in the dropdown, choose the starting and ending date, choose the status in the dropdown, click the search button | Pharmacy able to search and filter reception
PASSED | GAR-PUR 039 | Purchase - Reception - Edit | Pharmacy create reception | Click on the edit button in the action column, do edit in some field, click the save button | Pharmacy able to edit reception
PASSED | GAR-PUR 040 | Purchase - Return - Search | Pharmacy return GR | choose the category in the dropdown, choose the starting and ending date, click the search button | Pharmacy able to search and filter return
PASSED | GAR-PUR 041 | Purchase - Return - Export | Pharmacy return GR | Click on the export excel button | Pharmacy able to get the return excel file
PASSED | GAR-PUR 042 | Purchase - Return - Delete | Pharmacy return GR | Click on delete button in the action column | Pharmacy able to delete return

## Warehouse
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-WAR 001 | Compare Report Product Mutation vs Stock Opname | 1. Pharmacy make a stock opname for 1 product 2. Pharmacy is in Warehouse - History Stock Opname | 1. go to hostory SO 2. look at time of detail product 3. go to report 4. supply report 5. mutation report | product mutation report are show same time with Stock Opname time
PASSED | GAR-WAR 003 | Warehouse - Stock Opname - Filter Product Stock report | 1. Pharmacy must input the stock product 2. Pharmacy is in Warehouse - Latest Stock | 1. use the filter to filter by name, by product type, by stock product, by diagnostic categoty type | pharmacy able to see the latest stock report and also can filter the other stock report
PASSED | GAR-WAR 004 | Warehouse - Stock Opname - Filter Expired stock report | 1. Pharmacy must input expired date of each product 2. Pharmacy is in Warehouse - Stock Opname | 1. Choose filter kadaluarsa 2. Click Cari 3. Use the filter to showing the expired product by product name, by stock product, by status, by date | pharmacy able to see the expired stock of each product
PASSED | GAR-WAR 005 | Warehouse - Stock Opname - Using Stock Opname feature | 1. Pharmacy input product stock using stock opname, recetion feature, or first stock 2. Pharmacy is in Warehouse - Stock Opname - Stock Opname Baru | 1. Input correction of physical stock 2. click on verification 3. input the exact phyisical stock 4. click on verifikasi "verification" | Pharmacy able to make a correction of each product stock
PASSED | GAR-WAR 006 | Warehouse - Stock Opname - Using Moving Stock Feature | 1. Pharmacy must has more than 1 warehouse on the system 2. Pharmacy is in Warehouse - Moving Stock | 1. choose original warehouse 2. choose the product name 3. choose destination warehouse 4. input the amount of transfer 5. verification 6. pindahkan "move" | pharmacy able to transfer amount of product from original warehosue to another warehouse
PASSED | GAR-WAR 007 | Warehouse - Stock Opname - Using daftar gudang "warehouse list" feature | 1. go to warehouse 2. choose daftar gudang "warehouse list" 3. will showing the warehouse list pharmacy has in the system 4. choose tambah gudang "add warehouse" 5. input warehouse name 6. could choose between set the new warehouse become main warehouse to do reception & puchase or not 7. set to be active 8. simpan "save" | 1. go to warehouse 2. choose tambah gudang "add nwe warehouse" 3. input the mandatory and set it active 4. simpan "save" | Pharmacy able to has more than 1 warehouse and able to move the stock between warehouses
PASSED | GAR-WAR 008 | Warehouse - Stock Opname - Pop up | 1. after saving Puchase order 2. there pop up confimation of successfull | 1. after saving Puchase order 2. there pop up confimation of successfull | Pharmacy able to see the pop up notification ""1. after saving Puchase order 2. there pop up confimation of successfull "
PASSED | GAR-WAR 009 | Warehouse - Stock Opname - Import Stock Opname from Excel file | 1. Import Stock Opname using Excel file | 1. go to warehouse 2. go to stock Opname 3. go to impot 4. click download current stock to download excel format 5. fill the information 6. reimport the excel file | 1. pharmacy able to import stock opname excel file 2. pharmacy able to add new product using import excel for stock opname 3. If the adjustment product has no stock yet, Weighted Average are caluculated from purchase price column (harga beli) also from the excel file
PASSED | GAR-WAR 010 | Warehouse - Stock Opname - Nilai Persediaan |  | 1. Go to Stock Opname | Pharmacy able to see Nilai Persediaan column with 2 points of decimal
PASSED | GAR-WAR 011 | Warehouse - Stock Opname without Weighted Average | 1. Stock Opname product without weighted average | 1. Go to Stock Opname 2. Add new stock item | The Nilai Persedian should get from item price
PASSED | GAR-WAR 012 | Warehouse - Stock Opname with Weighted Average | 1. Stock Opname product with weighted average | 1. Go to Stock Opname 2. Add new stock item | The Nilai Persedian should get from weighted average
PASSED | GAR-WAR 013 | Warehouse - Stock Opname Table Responsive |  | 1. Go to Stock Opname 2. Set size of display to 100% | The table of stock opname is responsive and full displayed
PASSED | GAR-WAR 014 | Warehouse - Stock Opname - Same ED and Batch |  | 1. Go to Stock Opname 2. Create 2 SO with same ED and Batch | The stock opname should merge
PASSED | GAR-WAR 015 | Warehouse - Current Stock - Filter |  | 1. go to current stock 2. choose the warehouse in the dropdown,insert the product name, choose the product type and status in the dropdown | The current stock data should show up based on the chosen filter
PASSED | GAR-WAR 016 | Warehouse - Current Stock - Export Excel |  | Go to current stock and Click on the export excel button | Excel file has successfully downloaded
PASSED | GAR-WAR 017 | Warehouse - Expiration - Search |  | 1. go to expiration 2. insert the product name 3. click search | The expiration data should show up based on the product name
PASSED | GAR-WAR 018 | Warehouse - Expiration - Export Excel |  | Click on the export excel button | Excel file has successfully downloaded
PASSED | GAR-WAR 019 | Warehouse - Warehouse List - Unable to add warehouse |  | Go to warehouse list, click on the 'Add warehouse' button, leave out the name field | Warehouse failed to add with a pop up message that the name is required
PASSED | GAR-WAR 020 | Warehouse - Warehouse List - Edit warehouse |  | Go to warehouse list, click on the edit button in the action column, edit the warehouse details, click the save button | An edit at the warehouse detail has been made
PASSED | GAR-WAR 021 | Warehouse - Warehouse List - Search warehouse |  | Go to warehouse list, insert the warehouse name, choose the warehouse status, click on the search button | The warehouse list should show up based on the search input

## Report Navigation
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
UNCOVERED | GAR-REP-001 | Compare Sales Report - Invoice vs Payment type | Pharmacy create transaction on POS | 1. go to report --> sales report --> by invoice 2. go to report --> sales report --> by payment type 3. filter by March 4. see the total tagihan column 5. cross with by tagihan column by payment type | Compare Total Bill of the two reports
UNCOVERED | GAR-REP-002 | Compare Sales Report - Product vs Product type | Pharmacy create transaction on POS | 1. go to report --> sales report by product 2. filter the month 3. go to report --> sales report by product type 4. filter the month 5. make sure the qty are same | Compare Total Sales vs Total Bill per product in the filtered date
UNCOVERED | GAR-REP-003 | Compare Sales Report - Product vs Product type | Pharmacy create transaction on POS | USE GAR-REP-002 Data | Compare Product name of the same filter
PASSED | GAR-REP-004 | Download Report - Finance - Profit and Loss | Pharmacy create transaction on POS | 1. go to report --> accounting report --> p&l report --> filter the month --> download as excel | Check value of downloaded sheet vs dashboard table
PASSED | GAR-REP-005 | Download Report - Sale - Per Invoice | Pharmacy create transaction on POS | 1. go to report --> sales report by invoice --> fiter the month --> download as excel | Check value of downloaded sheet vs dashboard table
PASSED | GAR-REP-006 | Download Report - Sale - Per Product | Pharmacy create transaction on POS | 1. go to report --> sales report by product --> filter the month --> download as excel | Check value of downloaded sheet vs dashboard table
PASSED | GAR-REP-007 | General Report Integration | Pharmacy create GR | 1. go to report --> purchase report --> by product --> filter the month --> download as excel 2. go to GR --> click filter more --> filter the month --> download as excel 3. make sure the total amount of purchased are same | The total purchase of the month using GR and purchase report by product have same value
PASSED | GAR-REP-008 | Report - Finance - Balance sheet (Neraca) | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by ballance sheet | should show accounting report by ballance sheet 1. Checkout Transaction Cash 2. Checkout Transaction Inventory Value 3. Void Cash 4. Void Inventory Value 5. Return Cash 6. Return Inventory Value 7. Hutang Dagang
PASSED | GAR-REP-009 | Report - Finance - General Ledger | Pharmacy create transaction on POS | 1. go to report --> accounting report --> general ledger --> filter the month --> download to excel 2. filter by COGS only --> cross checking with COGS of trial balance and P&L report | pharmacy able to see COGS of general ledger are in the same amount with COGS in trial balance and P&L report
PASSED | GAR-REP-010 | Report - Finance - General Ledger | pharmacy create other income and expense | 1. go to report --> general ledger --> filter the date 2. make sure the journal are created | pharmacy able to create the journal for other income and expense 1. Goods Receipt Inventory Value 2. Goods Receipt Cash 3. Goods Receipt Hutang Dagang 4. Checkout Transaction Cash 5. Checkout Transaction Selling Discount 6. Checkout Transaction Selling Product 7. Checkout Transaction COGS 8. Checkout Transaction Inventory Value 9. Void Cash 10. Void Selling Discount 11. Void Selling Product 12. Void COGS 13. Void Inventory Value 14. Stock Opname Inventory Value 15. Stock Opname Adjustment Value 16. Supplier Inventory Value 17. Supplier Cash 18. Supplier Hutang Dagang
PASSED | GAR-REP-011 | Report - Finance - General Ledger | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by general journal | should show accounting report by general journal
PASSED | GAR-REP-012 | Report - Finance - Profit and Loss | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by profit and loss | should show accounting report by profit and loss 1. Checkout Selling Discount 2. Checkout Selling Product 3. Checkout COGS 4. Void Selling Discount 5. Void Selling Product 6. Void COGS 7. Adjustment Value
PASSED | GAR-REP-013 | Report - Finance - Trial Balance | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by trial ballance | should show accounting report by trial ballance 1. Goods Receipt Inventory Value 2. Goods Receipt Cash 3. Goods Receipt Hutang Dagang 4. Checkout Transaction Cash 5. Checkout Transaction Selling Discount 6. Checkout Transaction Selling Product 7. Checkout Transaction COGS 8. Checkout Transaction Inventory Value 9. Void Cash 10. Void Selling Discount 11. Void Selling Product 12. Void COGS 13. Void Inventory Value 14. Stock Opname Inventory Value 15. Stock Opname Adjustment Value 16. Supplier Inventory Value 17. Supplier Cash 18. Supplier Hutang Dagang
PASSED | GAR-REP-014 | Report - Preparation (Warehouse) - Log Product | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. warehouse report 3. by product log | should show warehouse report by product log 1. Invoice Number 2. Batch Number 3. Expiry Date 4. Supplier Name 5. Qty On Hand 6. Inventory Value
PASSED | GAR-REP-015 | Report - Preparation (Warehouse) - Probability | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. warehouse report 3. by probability | should show warehouse report by probability 1. Sold Qty 2. Packaging
PASSED | GAR-REP-016 | Report - Preparation (Warehouse) - Stock Mutation | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. warehouse report 3. by mutation stock | should show warehouse report by mutation report
PASSED | GAR-REP-017 | Report - Preparation (Warehouse) - Stock Opname | Pharmacy do stock opname | 1. go to report --> stock report --> stock opname report --> filter the month | pharmacy able to access stock opname report 1. Expiry Date 2. Batch Number 3. Physical Stock 4. System Stock 5. Qty Adjustment 6. Value Adjustment
PASSED | GAR-REP-018 | Report - Preparation (Warehouse) - Supply | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. warehouse report 3. by supply | should show warehouse report by supply 1. Purchase Qty 2. Sold Qty 3. Qty on Hand 4. Void Qty 5. Inventory Name 6. System Stock 7. Packaging 8. Qty Adjustment 9. Inventory Value 10. Return Qty
PASSED | GAR-REP-019 | Report - Purchase - Per Bill Payment | 1. Pharmacy create transaction on Reception module 2. Pharmacy set the payment with debit or credit on reception module | 1. click report 2. Purchase report 3. by bill payment | should show purchase report by bill payment from reception module 1. Invoice Number 2. Net Price 3. Supplier Name 4. Product Name 5. Purchase price 6. Return qty 7. Packaging 8. Total return
PASSED | GAR-REP-020 | Report - Purchase - Per Product | Pharmacy set the payment with debit or credit on reception module | 1. click report 2. Purchase report 3. by product | should show purchase report by product from reception module 1. Invoice Number 2. Purchase Qty 3. Purchase Price 4. Discount 5. Net Price 6. Supplier Name 7. Packaging
PASSED | GAR-REP-021 | Report - Purchase - Per Supplier | 1. Pharmacy set the payment with debit or credit on reception module 2. Pharmacy set the supplier name on reception module | 1. click report 2. Purchase report 3. by supplier | should show purchase report by supplier from reception module 1. Invoice Number 2. Purchase Qty 3. Purchase Price 4. Discount 5. Net Price 6. Supplier Name 7. Packaging
PASSED | GAR-REP-022 | Report - Purchase - Return | 1. Pharmacy set the payment with debit or credit on reception module 2. Pharmacy set the supplier name on reception module | 1. click report 2. Purchase report 3. by supplier | should show purchase report by supplier from reception module 1. Invoice Number 2. Purchase Qty 3. Purchase Price 4. Supplier Name 5. Packaging
PASSED | GAR-REP-023 | Report - Sale - Per Customer | 1. Pharmacy set their own username 2. Pharmacy input customer name in transaction | 1. click report 2. selling report 3. by customer | should show selling report by customer name from cashier transaction 1. Sold Qty 2. Packaging 3. Total Sales 4. Total Net Sales 5. Customer Name
PASSED | GAR-REP-024 | Report - Sale - Per Doctor | 1. Pharmacy set their own username 2. Pharmacy input doctor name in transaction | 1. click report 2. selling report 3. by doctor | should show selling report by doctor from cashier transaction 1. Invoice Number 2. Discount 3. Total Sales 4. Total Net Sales 5. Other Income 6. Customer Name 7. Doctor Name
PASSED | GAR-REP-025 | Report - Sale - Per Invoice | 1. Pharmacy create debt transaction on cashier 2. Pharmacy create debt payment on cashier | 1. go to report --> sales report --> by invoice 2. filter the month | pharmacy able to see the debt payment report in the sales report by invoice
PASSED | GAR-REP-026 | Report - Sale - Per Invoice | Pharmacy create transaction on POS | 1. click report 2. selling report 3. by invoice | should show selling report by invoice from cashier transaction 1. Invoice Number 2. Packaging 3. Discount 4. Total Sales 5. Total Sales + rounding 6. Total Net Sales 7. Change 8. Other Income 9. Customer Name
PASSED | GAR-REP-027 | Report - Sale - Per Payment Type | 1. Pharmacy create transaction on POS 2. Pharmacy set the payment by using cash, debet, or online payment method | 1. click report 2. selling report 3. by payment method | should show selling report by payment method from cashier transaction 1. Invoice Number 2. Total Net Sales 3. Payment Type 4. Customer Name 5. Cashier Name
PASSED | GAR-REP-028 | Report - Sale - Per Prescription | 1. Pharmacy set their own username 2. Pharmacy input prescription in transaction | 1. click report 2. selling report 3. by prescription | should show selling report by prescription from cashier transaction 1. Invoice Number 2. Discount 3. Total Sales 4. Total Net Sales 5. Other Income 6. Customer Name 7. Cashier Name 8. Doctor Name
PASSED | GAR-REP-029 | Report - Sale - Per Product | Pharmacy create transaction on POS | 1. click report 2. selling report 3. by product | should show selling report by product from cashier transaction 1. Invoice Number 2. Sold Qty 3. Qty on Hand 4. Packaging 5. Discount 6. Total Sales 7. Total Net Sales 8. Cashier Name
PASSED | GAR-REP-030 | Report - Sale - Per Product | Pharmacy create transaction on POS | 1. go to report --> sales report by product 2. make sure there is row for pembulatan | Pharmacy able to see the pembulatan row
PASSED | GAR-REP-031 | Report - Sale - Per Product | 1. Pharmacy create transaction on POS 2. Pharmacy input discount on POS 3. harmacy input discount for whole invoice on POS | 1. go to report --> sales report by product 2. filter the month 3. make sure there is dicount column and nett sales column | pharmacy able to see discount column and nett sales column in the report
PASSED | GAR-REP-032 | Report - Sale - Per Product | Pharmacy create transaction on POS | 1. go to report --> sales report --> by product 2. scroll down to find the round row | pharmacy able to see the total amount of round by system in cashier by using sales report by product (Round up should be nearest hundreds)
PASSED | GAR-REP-033 | Report - Sale - Per Product | 1. Pharmacy set their own username 2. Pharmacy set type of the product list | 1. click report 2. selling report 3. by product type | should show selling report by product type from cashier transaction
PASSED | GAR-REP-034 | Report - Sale - Per Return | 1. Pharmacy set their own username 2. Pharmacy input customer name in transaction | 1. click report 2. selling report 3. by return | should show selling report by return from cashier transaction 1. Invoice Number 2. Sold Qty 3. Packaging 4. Total Sales
PASSED | GAR-REP-035 | Report - Sale - Per Void | 1. Pharmacy create transaction on POS 2. Pharmacy void the transaction | 1. click report 2. selling report 3. by void | should show selling report by void from cashier transaction 1. Invoice Number 2. Discount 3. Total Sales 4. Change 5. Other Income 6. Void Qty 7. Total Void 8. Discount 9. Change
| GAR-REP-036 | Report - Warehouse (Warehouse) - Supply | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. warehouse report 3. by supply | 1. The report didn't contains minus stock 2. Calculated Weighted Average for Stock adjustment (stock opname module) 3. The Inventory value should be zero (0) if the current stock are zero (0)
| GAR-REP-037 | Report - Accounting - P&L report | For new Pharmacy the there is new COA called (6120 - Penyesuaian Stok) | 1. Login to new Pharmacy 2. go to accounting --> account 3. make sure the new COA are applied in the list | 1. Stock Opname adjustment using new COA 2. Stock Opname Adjustment are not using COGS anymore 3. Stock Adjustment (+) make the COA Increased 4. Stock Adjustment (-) make the COA decreased
| GAR-REP-038 | Report - Accounting - General Ledger | For Stock Adjustment (Stock Opname) there is new COA 6120 - Penyesuaian Stok | 1. click report 2. accounting report 3. general ledger | 1. stock opname using new COA 6120 - Penyesuaian Stok
| GAR-REP-039 | Report - Accounting - Trial Balance | For Stock Adjustment (Stock Opname) there is new COA 6120 - Penyesuaian Stok | 1. click report 2. accounting report 3. Trial Balance | 1. stock opname using new COA 6120 - Penyesuaian Stok
| GAR-REP-040 | Report - Warehouse | Total stock qty on warehouse report by supply and by mutation report | 1. click report 2. go to warehouse report 3. by supply 4. by mutation report 5. should filter the same date range and warehouse | 1. total qty of stok akhir in warehouse report by supply should same with stock avaliable in warehouse report by mutation
PASSED | GAR-REP-041 | Report - Sales report by cashier | Config (dev) - Sales Report - OFF | 1. click report 2. go to sales report 3. make sure sales report by cashier are hidden | Sales report by cashier are hidden
PASSED | GAR-REP-042 | Report - Sales Report by Shift | Config (dev) - Sales Report - OFF | 1. click report 2. go to sales report 3. make sure sales report by shift are hidden | Sales report by shift are hidden
PASSED | GAR-REP-043 | Report - Sales report by product type | Config (dev) - Sales Report - OFF | 1. click report 2. go to sales report 3. make sure sales report by product type are hidden | Sales report by product type are hidden
PASSED | GAR-REP-044 | Report - Sales Report by Drug Classification | Config (dev) - Sales Report - OFF | 1. click report 2. go to sales report 3. make sure sales report by drug classification are hidden | Sales report by drug classification are hidden
PASSED | GAR-REP-045 | Report - Purchase report by drug classification | Config (dev) - Sales Report - OFF | 1. click report 2. go to purchase report 3. make sure purchase report by drug classification are hidden | Purchase report by drug classification are hidden
PASSED | GAR-REP-046 | Report - Sales report by audit | Config (dev) - Sales Report - OFF | 1. click report 2. go to sales report 3. make sure sales report by audit are hidden | sales report by audit are hidden
PASSED | GAR-REP-047 | Report - Sales report by void per product | Config (dev) - Sales Report - OFF | 1. click report 2. go to sales report 3. make sure sales report by void per product are hidden | sales report by void per item are hidden
PASSED | GAR-REP-048 | Report - Preparation (Warehouse) - Pareto | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. warehouse report 3. by pareto | should show warehouse report by pareto 1. Sold Qty 2. Total Sales
| GAR-REP-049 | Report - Finance - Ledger | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by ledger - Summary | should show accounting report by ledger 1. Goods Receipt Inventory Value 2. Goods Receipt Cash 3. Goods Receipt Hutang Dagang 4. Checkout Transaction Cash 5. Checkout Transaction Selling Discount 6. Checkout Transaction Selling Product 7. Checkout Transaction COGS 8. Checkout Transaction Inventory Value 9. Void Cash 10. Void Selling Discount 11. Void Selling Product 12. Void COGS 13. Void Inventory Value 14. Supplier Inventory Value 15. Supplier Cash 16. Supplier Hutang Dagang
| GAR-REP-050 | Report - Finance - Ledger | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by ledger - Details | should show accounting report by ledger in details
| GAR-REP-051 | Report - Finance - Ledger | Pharmacy create transaction on cahsier, reception, return, stock opname, accounting module | 1. click report 2. accounting report 3. by ledger - Details 4. Download as Excel | Pharmacys should able to export excel report
| GAR-REP-052 | Report - Purchase report per Product | Pharmacy create transaction on POS | 1. go to report --> sales report --> by product | should show : 1. Purchase qty 2. Return qty 3. Net purchase qty 4. Grand total
| GAR-REP-053 | Report - Purchase report per Product - export as pdf | Pharmacy create transaction on POS | 1. go to report --> sales report --> by product | Able to export as pdf
| GAR-REP-054 | Report - Purchase report per Product - export as excel | Pharmacy create transaction on POS | 1. go to report --> sales report --> by product | Able to export as excel
| GAR-REP-055 | Compare discount in Sales Report - Invoice vs product vs P&L | Pharmacy create transaction on POS | 1. go to report --> sales report --> by invoice 2. go to report --> sales report --> by product 3. go to report --> accounting --> P&L 4. see the total tagihan column 5. cross with by tagihan column by payment type | Compare Total Discount of the three reports
| GAR-REP-056 | Compare Sales Report - Balance vs Trial Balance | Pharmacy create GR and Transaction | 1. go to report --> accounting -> Balance 2. filter the month 3. go to report --> accounting -> Trial Balance 4. filter the month | Number of two report have same value
| GAR-REP-057 | Compare Sales Report - Trial Balance |  | 1. go to report --> accounting -> Trial Balance 2. filter the month | pharmacy able to see beginning balance column
PASSED | GAR-REP-058 | Report - Preparation (Warehouse) - Probability Load More | Pharmacy create transaction on POS | 1. go to report --> Preparation -> Probability 2. filter the month (1 May - 1 august) | Load more button didnt display in 100 data | pharmacy 3
PASSED | GAR-REP-059 | Report - Finance - COGS | Pharmacy create transaction on POS | 1. go to report --> Finance -> Trial Balance 2. go to report --> Finance -> General Ledger 3. go to report --> Finance -> Ledger 4. go to Finance --> P&L 5. filter the month | pharmacy able to see COGS of ledger are in the same amount with COGS in general ledger, trial balance and P&L report
PASSED | GAR-REP-060 | Report - Finance - Ledger account inventory | Pharmacy create transaction on POS | 1. go to report --> Finance -> Ledger 2. filter the month | inventory value in the Ledger should use weighted average calculation
PASSED | GAR-REP-061 | Report - Finance - Ledger Profit and Loss | Pharmacy create transaction on POS | 1. go to report --> Finance -> Ledger 2. go to dashboard | Total P&L chart in dashboard in the same amount with the total P&L in ledger
| GAR-REP-062 | Report - Sales - Download pdf Per invoice | Pharmacy create transaction on POS | 1. go to per invoice 2. choose the start and end data date 3. click 'show' button 4. click 'pdf' button | successfully download the sales per invoice pdf file based on the selected date
| GAR-REP-063 | Report - Sales - Download pdf Per payment type | Pharmacy create transaction on POS | 1. go to per payment type 2. choose the start and end data date 3. click 'show' button 4. click 'pdf' button | successfully download the sales per payment type pdf file based on the selected date
| GAR-REP-064 | Report - Sales - Download pdf Per sales | Pharmacy create transaction on POS | 1. go to per sales 2. choose the start and end data date 3. click 'show' button 4. click 'pdf' button | successfully download the sales per sales pdf file based on the selected date
| GAR-REP-065 | Report - Sales - Download pdf Per void | Pharmacy create transaction on POS | 1. go to per void 2. choose the start and end data date 3. click 'show' button 4. click 'pdf' button | successfully download the sales per void pdf file based on the selected date
| GAR-REP-066 | Report - Sales - Download pdf Per recipe | Pharmacy create transaction on POS | 1. go to per recipe 2. choose the start and end data date 3. click 'show' button 4. click 'pdf' button | successfully download the sales per recipe pdf file based on the selected date

## Settings
TEST RESULTS | TEST CASE ID | TEST SCENARIO | TEST SUITE | TEST PROCEDURE | EXPECTED RESULTS | REMARKS
PASSED | GAR-SET 001 | Setting - User Detail | Pharmacy has 2 credentials (admin and ceo) by defaults | 1. go to setting 2. click user 3. go to action 4. click button details / pen button | Pharmacy able to see the user details
PASSED | GAR-SET 002 | Setting - Edit User | Pharmacy has user credential such as cashier, inventory, accounting | 1. go to setting 2. click user 3. go to action 4. click button details / magnifitying glass 5. click pen button 6. make changes such as group, username, password changes, active/diactive | Pharmacy able to edit credential login
PASSED | GAR-SET 003 | Setting - Edit User | Pharmacy has user credential such as cashier, inventory, accounting | 1. go to setting 2. click user 3. go to action 4. click pen button 6. make changes such as group, username, password changes, active/diactive | Pharmacy able to edit credential login
PASSED | GAR-SET 004 | Setting - Delete User | Pharmacy has more than 1 user credential | 1. go to setting 2. click user 3. go to action 4. click on trash button | Pharmacy able to delete user credential
PASSED | GAR-SET 005 | Setting - add new user |  | 1. go to setting 2. click user 3. add new user 4. choose the user group 5. input username 6. choose contact 7. input password 8. repeat the password 9. choose active / draft | Pharmacy able to add new user credential
| GAR-SET 006 | Setting - User Privilege | Pharmacy has 4 group og user (Management, cashier,inventory, accounting) by defaults | 1. go to setting 2. click user 3. click group 4. click key button on action column 5. set the group of user privilege | Pharmacy able to set privilege for every group of user and able to access the module
| GAR-SET 007 | Setting - Configuration of business profil e |  | 1. go to setting 2. click configuration 3. go to business profile column 4. pharmacy must set pharmacy name, email of pharmacy, bank account, bank number, name of bank account 5. the other are optional | 1. when set the pharmacy name are impact to pharmacy title 2. when set the optional column such address are impact to POS and reception Print preview 3. when set the SIA, SIPA number are impact to POS and reception preint preview 4. when upload pharmacy logo are impact to reception print preview
PASSED | GAR-SET 008 | Setting - Shift Configuration | Pharmacy has 3 shift active configuration by defaults | 1. go to setting 2. click configuration 3. go to shift column 4. set the shift name, shift time schedule 5. save | Pharmacy able to set the shift time
PASSED | GAR-SET 009 | Setting - Print Preview | Pharmacy set the SIA number | 1. go to setting 2. click configuration 3. go to print preview 4. Set Footer Text 5. Choose to view or hide receipt product details 6. choose the void information 7. choose to view tuslah, embalage, etc 8. choose to view SIA number 9. choose to view price per item | 1. Pharmacy able to choose print size mini, medium, wide paper 2. Pharmacy ablt to choose to view the receipt 3. Pharmacy able to choose to view sia number 4. Pharmacy able to choose to view price per item
PASSED | GAR-SET 010 | Setting - Cashier Configuration |  | 1. go to setting 2. click configuration | Pharmacy able to set cashier configuration
PASSED | GAR-SET 011 | Setting - Application Information |  | 1. go to setting 2. click configuration | The Setting didnt contains tab Application Information
PASSED | GAR-SET 012 | Setting - Non tunai Payment |  | 1. go to setting 2. click on configuration 3. go to non tunai payment 4. Set bank/ online payment 5. input name of payment 6. input minimum payment 7. input maximum payment 8. set active or inactive | Pharmacy able to add online/ bank payment Pharmacy able to see the non tunai payment on POS (debet payment)
| GAR-SET 013 | Setting - Change Log |  | 1. go to setting 2. click on configuration 3. go to change log | Pharmacy able to see the changes update

## Options (hidden)
Test Case ID | Test Scenario | Categories | Pre-requisite | Test Procedure | Expected Results | Test Results | Jira Ticket | Automation Status | Remarks
PH-MO-001 | More Options |  | Given user is in homepage | WHEN user clicks more option menu (tripple dots HAHA) | THEN there are options should show | Not Tested |  |  | More options/ellipsis doesn't exist
PH-MO-002 | Help and Support |  | Given user is in more option menu | WHEN user clicks the Help and Support option | THEN it should go and load the Help and Support Page. | Not Tested |  |  | More options/ellipsis doesn't exist
PH-MO-003 |  |  | Given user is in Help and Support Page | WHEN user clicks "CLICK HERE TO CONTACT US" | THEN a SWIPERX conversation window / Message Window should appear. WHERE user can send a message to SWIPERX team. | Not Tested |  |  | There is no conversation window but a new page appears saying "Our team is happy to answer your questions...."
PH-MO-004 |  |  | Given user is in the Message Window / SWIPERX conversation window | WHEN user try to create a message to SwipeRx. AND user clicks the send button on the conversation window. | THEN a message / reply should appear coming from a BOT saying "SwipeRx will reply as soon as they can." | Not Tested |  |  | There is no conversation window.
PH-MO-005 |  |  | Given user is in the Message Window / SWIPERX conversation window | WHEN user clicks the "x" button of the SwipeRx conversation message / Message Window | THEN the SwipeRx conversation window / Message window should be remove / disappear | Not Tested |  |  | There is no conversation window.
PH-MO-006 |  |  | Given user is in Help and Support Page | WHEN user clicks "Back arrow" | THEN it should go back to the homepage | Not Tested |  |  | Back arrow doesn't exist
PH-MO-007 | EXIT |  | Given user is in more option menu | WHEN user clicks "Exit" | THEN it should exit and go to swipeRx | Pass |  |  | More options/ellipsis doesn't exist
PH-MO-008 | Start Tour |  | Given user is in more option menu | WHEN user clicks "Start Tour" | THEN a tour window should appear. AND start the tour. | Pass |  |  | More options/ellipsis doesn't exist

## Index
RESULT | RESULT DESCRIPTION
PASSED | No issue
FAILED | Issue found
DEFERRED | Planned but not executed
UNCOVERED | Removed in regression scope
IN PROGRESS | Currently handling